## Slide 1: Calgary’s Winter PIT
November 2015
PiT Count Coordinator Training Workshop
Meaghan Bell
Module 3 – Planning for Success

## Slide 2: Background
Calgary’s PiT occurred biannually in May between 1992-2008 coordinated by City of Calgary
2012 CHF took over role of coordination, undertook international review of PiT methodologies
Decision to align with HUD for January Count
Assumption:
  shelter and facility counts would be more accurate as shelter stayers return to the shelters earlier to secure their spot
  cold temperatures would bring rough sleepers inside

## Slide 3: Winter 2012 count
Planning:
  Consultation with outreach teams, CPS, Calgary bylaw services to identify active camps
  Assessing occupancy at emergency shelters
  Outreach to local businesses for donations and supplies (sleeping bags, jackets, hand warmers)
  Communication to volunteers re: weather updates, appropriate dress and weather exposure

## Slide 4: Week of January 18, 2012
Extreme cold weather – temperatures around -35
Exploring conditions for which PiT would be cancelled with partners (Calgary Police and outreach teams)
Tracking shelter utilization and assessing number of potential beds for transport night of the count and planning for people who were barred from shelters
Logistics:
  recruiting additional volunteers and vehicles
  Re-arranging teams
  Swapping pens for pencils for street surveys

## Slide 5: Night of the count
Count went on, 10 p.m. -1 a.m
-37
160 volunteers
Every team had a vehicle to drive to their zones
All volunteer teams were in the inner city and encouraged to go into open businesses (Tim Horton’s, McDonalds, to warm up)
Transportation crews available for people encountered who wanted to go to a shelter
Notes: Strengths of winter count: Volunteer enthusiasm
Community awareness about rough sleepers and homelessness in Calgary; media attention; partnering with businesses; equity in how people were approached; engagement with entrenched rough sleepers

## Slide 6: Winter count strengths
Drew attention to emergency planning
Volunteer enthusiasm
Community awareness (volunteers, interactions night of, local businesses, media)
Engagement with most entrenched rough sleepers
Equity in how, and who was approached the night of the count
Notes: *also more equity in how people were approached in the streets

## Slide 7: Shelter from the storm
“when overnight temperatures fall to extreme levels, the number of rough sleepers who have moved into shelters is equal to 7% of the average number of overnight shelter stays…winter temperatures between 0 C and -10 C and precipitation has a particularly strong effect on moving rough sleepers indoors. Those conditions have have caused movements of rough sleepers into shelters; a temporary but unexpected inflow equal to 10-15% of the average number of shelter users” – Kneebone, 2014.
http://policyschool.ucalgary.ca/sites/default/files/research/weather-and-homeless-kneebone-jadidzadeh.pdf
Notes: Quick summary of recent report in Calgary tracking shelter utilization and weather patterns over multiple years – used as supplement in PiT planning

## Slide 8: Winter 2012 & 2014